## Slide 1
AAROGYA VAANI
MVP Implementation Plan
Focused Use Case · Tech Stack · 3-Month Delivery | Jun – Aug 2026
1
Core Use Case
4
Tech Components
13
Weeks to Deliver
2+
Pilot CHO Sites
IIM Visakhapatnam · Chief Digital & AI Officer Program · Group 6 · 2026

## Slide 2
THE PROBLEM WE ARE SOLVING
Context for the MVP scope
1:10,000
Doctor-patient ratio
in rural India
40–80
Patients a CHO sees
per day with no tools
0%
Patient notes
are digitised today
No Decision Support
CHOs diagnose under crushing cognitive load — no clinical prompts, no guidelines at hand.
No Digital Records
Hand-written registers mean zero continuity of care when a patient moves between facilities.
Wrong Escalations
Hospitals clogged with manageable cases while critical referrals get missed entirely.

## Slide 3
THE MVP USE CASE — VOICE-GUIDED TRIAGE FOR FEVER & RESPIRATORY ILLNESS
Chosen for high prevalence, clear protocol, and minimum integration complexity
WHY THIS USE CASE?
1
70% of CHO caseload
Fever, cough, breathlessness are the most common presenting complaints — maximum real-world impact.
2
Clear WHO protocol
IMCI triage for ARI and fever is a well-defined, tested clinical flowchart — no ambiguity to model.
3
Minimum integrations
No IoT sensors required for v1. Voice + basic BP manual entry + WhatsApp follow-up is sufficient.
4
Single language first
Tamil-only for the pilot in Chennai-region Arogya Mandirs — cuts multilingual complexity by 80%.
5
Measurable accuracy
IMCI protocol has clear red-flag criteria — easy to validate AI output against known clinical benchmarks.
THE SCENARIO — STEP BY STEP
1
Patient arrives at Arogya Mandir
CHO opens Aarogya Vaani app on a basic Android phone/Webapp*.
2
Voice triage begins
App speaks to patient in Native Language(English, Hindi): age, symptoms, duration, severity. NLP extracts structured data.
3
Manual vitals entry
CHO enters BP & SpO2 from existing equipment. App flags danger values.
4
SOAP note generated
AI produces Subjective-Objective-Assessment-Plan in under 10 seconds. CHO reviews & approves.
5
Escalation decision
App recommends: Treat at home / PHC referral / Emergency.)
Auto-drafts WhatsApp message to family (Whatsapp - Out of scope for MVP).
6
Day-3 follow-up (Whatsapp Out of Scope for MVP)
Automated WhatsApp message checks patient status. Non-response flags back to CHO.

## Slide 4
MVP SCOPE — WHAT'S IN AND WHAT'S OUT
Deliberate constraints to deliver something real in 13 weeks
✓ IN SCOPE — MVP v1
Voice triage in Tamil (single language)
Fever + Respiratory illness IMCI protocol
Manual vitals entry (BP + SpO2 + Diabetic + Thermometer)
AI-generated SOAP note (CHO review + approve)
3-tier escalation: Home / PHC / Emergency
WhatsApp follow-up at Day 3 (out of scope)
Simple web dashboard for CHO (case log) ***
Pilot at 2 Arogya Mandirs
✗ OUT OF SCOPE — Future Phases
Bluetooth IoT device auto-sync (Phase 2)
Multi-language support — 5 more languages
ABHA / National Health Stack integration
Teleconsult slot auto-booking
District-level analytics dashboard
Maternal & child health use cases
Outbreak / epidemic signal detection
FHIR-compliant longitudinal records

## Slide 5
TECH STACK — CHOSEN FOR SPEED, OPEN-SOURCE & CHO-GRADE RELIABILITY
All components are free/open-source or have generous free tiers — no licensing cost for MVP
FRONTEND — CHO App
React Native (Expo)
Cross-platform Android/iOS. Single codebase. Expo Go for rapid testing.
Voice UI via expo-speech + expo-av
Text-to-Speech for Tamil prompts; Audio recording for patient responses.
Offline-first with SQLite
Works in low-connectivity areas. Syncs when internet is available.
BACKEND — API & Logic
FastAPI (Python)
Lightweight REST API. Handles SOAP generation, escalation logic, and case storage.
PostgreSQL
Case records, CHO profiles, triage history. Hosted free on Supabase for MVP.
Celery + Redis (Whatsapp Out of scope?)
Async task queue for WhatsApp follow-up scheduling (day 3 triggers).
AI / NLP — Triage Engine
OpenAI Whisper (ASR)
State-of-the-art speech-to-text. Engish, Hindi language support. Runs on CPU.
GPT-4o (via API) / Llama 3 local
Symptom extraction + SOAP note generation. Fallback: fine-tuned Llama 3 on-device.
LangChain + IMCI decision tree
Structured clinical workflow. LLM constrained by IMCI rule-based logic for safety.
MESSAGING & INFRA
WhatsApp Business API (Twilio) [Whatsapp Out of scope]
Day-3 follow-up messages. Free 1000 conversations/month on WhatsApp Cloud API.
Docker + Railway / Render
Containerised deployment. Free tier sufficient for MVP traffic. CI/CD via GitHub Actions.
Supabase (Auth + Storage)
CHO login, case media storage. Free tier: 500MB DB, 1GB file storage.

## Slide 6
MVP SYSTEM ARCHITECTURE
How the components connect — data flow for a single triage session
MVP SYSTEM ARCHITECTURE
How the components connect — data flow for a single triage session
CHO Android App
(React Native)
Voice Engine
(Whisper ASR)
FastAPI
Backend
LLM + IMCI
Triage Logic
PostgreSQL
(Supabase)
SOAP Note
Generator
WhatsApp
Follow-Up (Out of Scope)
CHO Dashboard
(Web)
1 Voice input
2 Transcribe + extract
3 IMCI logic
4 Store + generate
5 Notify + log
Patient → CHO app → Voice engine → FastAPI → LLM triage → SOAP note → Escalation → WhatsApp follow-up → Dashboard

## Slide 7
13-WEEK IMPLEMENTATION PLAN | 1 Jun – 31 Aug 2026
Three sprints — each with clear team ownership and exit criteria
SPRINT 1 — Foundation
1 Jun – 28 Jun (Weeks 1–4)
Wk 1–2
Clinical protocol mapping — digitise IMCI fever/ARI decision tree (M5+M6)
Wk 1–2
App scaffolding — React Native Expo project, navigation, auth screens (M3+M4)
Wk 2–3
Whisper ASR integration — Tamil STT working on test phrases (M3+M4)
Wk 3–4
FastAPI backend + PostgreSQL schema on Supabase (M7+M1)
Wk 4
Voice prompt script writing in Tamil with clinical advisor (M5+M6)
EXIT ✓
Voice app records patient speech → transcribes → returns structured symptom JSON
SPRINT 2 — Build Core
29 Jun – 26 Jul (Weeks 5–8)
Wk 5–6
IMCI triage engine — LangChain + GPT-4o with IMCI rules as constraints (M3+M4)
Wk 5–6
SOAP note generator — prompt engineering + CHO approval flow (M3+M4)
Wk 6–7
Manual vitals entry UI + danger-value alert logic (M5+M6)
Wk 7–8
Escalation output (3-tier) + WhatsApp API integration via Twilio (M7+M1)
Wk 8
End-to-end integration test — full triage session on staging (All pairs)
EXIT ✓
Full triage session completes in < 5 min. SOAP note generated. Escalation sent.
SPRINT 3 — Pilot & Validate
27 Jul – 31 Aug (Weeks 9–13)
Wk 9
CHO onboarding training at 2 Arogya Mandirs (M1+M2, M5+M6)
Wk 9–10
Live pilot — 20+ real triage sessions per site (All pairs)
Wk 10–11
Accuracy validation — AI vs clinical advisor review of SOAP notes (M5+M6)
Wk 11–12
Bug fixes, CHO feedback incorporation, WhatsApp follow-up check (M3+M4)
Wk 13
Final report, demo video, capstone presentation (M1+M2)
EXIT ✓
≥85% SOAP accuracy. CHO satisfaction ≥4/5. Pilot data presented.

## Slide 8
TEAM OWNERSHIP — WHO BUILDS WHAT
Mapped to the 4 paired workstreams from the project plan
M1 + M2
Project Lead & Strategy
Sprint planning, weekly standups, risk log
CHO onboarding coordination at pilot sites
Final capstone report & demo presentation
Stakeholder communication & milestone sign-off
🗓 PM across all sprints · Sprint 3: pilot logistics & delivery
M3 + M4
AI/ML, NLP & Voice UX
Whisper ASR integration — Tamil speech-to-text
LangChain + GPT-4o IMCI triage engine
SOAP note generator — prompt engineering
React Native voice UI & triage conversation flow
🗓 Sprint 1: ASR + app scaffold · Sprint 2: triage engine + SOAP · Sprint 3: accuracy testing
M5 + M6
IoT Integration & Clinical
IMCI fever/ARI protocol — digitise decision tree
Manual vitals entry UI + danger-value alerts
Clinical validation of AI SOAP note output
Hindi/English voice prompt script with clinical accuracy
🗓 Sprint 1: protocol mapping · Sprint 2: vitals + alerts · Sprint 3: clinical validation
M7 + M1
Data Architecture & Follow-Up
FastAPI backend + PostgreSQL schema (Supabase)
Case record storage & retrieval API
WhatsApp follow-up workflow — Twilio integration (Out of scope)
CHO web dashboard — case log & status view
🗓 Sprint 1: DB schema + API · Sprint 2: WhatsApp + dashboard · Sprint 3: data reporting

## Slide 9
SUCCESS METRICS & KEY RISKS
How we measure MVP success and what could go wrong
MVP SUCCESS METRICS
≥85%
SOAP note clinical accuracy
vs clinical advisor review
<5 min
End-to-end triage session
duration per patient
≥4/5
CHO satisfaction score
post-pilot survey
40+
Real triage sessions
completed at pilot sites
Day 3
Follow-up message sent
& non-responders flagged
RISKS & MITIGATIONS
!
Whisper ASR accuracy in Tamil dialects
→ Pre-test on 5 CHO voices; fine-tune on domain words; add manual correction option
!
GPT-4o API costs for 40+ sessions
→ Cache common IMCI patterns; use Llama 3 local as fallback; budget ₹5k cap
!
CHO reluctance to use a new tool
→ Co-design 2 sessions before pilot; keep UI under 3 taps to any action
!
WhatsApp approval for business API
→ Apply Week 1; use Twilio sandbox for testing; SMS as backup
!
Network outage at Arogya Mandir
→ SQLite offline cache; auto-sync when connected; no data lost

## Slide 10
THE PLAN IN THREE SENTENCES
Build a voice-first Hindi/English triage app
for fever and respiratory illness.
Test it live with real CHOs at 2 Arogya Mandirs.
Prove ≥85% clinical accuracy. Then scale.
1 Jun
Start
13 Wks
Duration
HINDI/ENGLISH
Language v1
31 Aug
Delivery
IIM Visakhapatnam · Chief Digital & AI Officer Program · Group 6 · 2026